Neighbourhood Plan Working Group

Draft Minutes of Fourth Meeting, 4th August 2026

Present:

Phil Goodier	(PG)		Group Chair

David Gluck	(DG)		Consultant

Dean Culshaw	(DC)		BMPC Chair

Rupert Scales	(RS)		BMPC Councillor / Heritage & Local Character sub-group lead

James Hobson	(JH)		Housing Provision and Affordability sub-group lead

Jane Fowler 	(JF)		Communications sub-group lead

Rod Hepple-Willson (RHW)	Transport and access sub-group lead

Chris Edmondson (CE)		Flooding & Utilities Capacity sub-group lead

Richard Houseman (RH)	Community Facilities sub-group lead

Paul Collinson	(PC)		Green Spaces sub-group lead

- Apologies

(None)

- Minutes of the last meeting, 30th April 2026

These were accepted as a correct record.

- Parish Council Meeting Feedback

The sub-group structure and leads is supported.  We have approval to spend the first £1,500 on the Adept Consulting Work.  The Clerk has confirmed that she has delegated authority to proceed with suitable expenditure recommended by this team without PC approval – although this will still be sought for larger costs.

- Matters arising and Action Review

Actions

| # | Action | Who | When | Status |
| --- | --- | --- | --- | --- |
| Previous Meetings |  |  |  |  |
| 1.12 | A paper communications route will be set up for the digitally excluded | JF | TBC | In communications plan – consider complete here. |
| 1.10 | Identify NYC Planning contact / support | Sue Reid | April 23rd | Complete – Joan Jackson. PG / DG met in July. |
| 2.9 | Prepare briefs for Sub Groups before 20th June | DG | 15th June | Complete |
| 2.10 | Notify other stakeholders of the decision to produce a NP | Clerk | 15th May | DG to prepare a list of stakeholders – Complete. DG / JF to draft the letter – Complete. Sue to send out on behalf of the PC – Unsure – PG to chase. |
| 10th June 2026 Meeting |  |  |  |  |
| 3.1 | Put updated project plan on website | DG / PG | 15th May | Complete and updated again for this meeting. |
| 3.2 | Set up FB account for NDP | JF | 31st May | Complete |
| 3.3 | Set up YouTube channel for NDP and post videos publicising 20th June | JF | 15th May | Complete |
| 3.4 | Meet village organisations (e.g. WI, Coffee Mornings, Churches) to talk about NHP | JF / PG | Ongoing | Ongoing |
| 3.5 | Put regular updates in the Parish Magazine | JF / PG | August – for September edition | Complete / Ongoing – drop from here as in Comms plan |
| 3.6 | Set up OneDrive account | PG | 30th June | Partially complete – PG to move to PC domain |
| 3.7 | Set up a register of all the comms we have done (retrospective & ongoing) | JF | 30th June | Complete / Ongoing – drop from here as in Comms plan |
| 3.8 | Approach the History Group to ask them to support the Heritage & Local Character WG | RS | 20th June | Compete – David Derbyshire attended the last meeting |
| 3.9 | Approach Rod Hepple-Wilson (Community facilities) and Jackie Holder (Transport) about the two remaining sub-group leads | PG | 11th June | Complete – Rod now leads transport. Richard now leads community facilities. |
| 3.10 | Approach agreed people about sub-group membership before 20th June | PG | 15th June | Complete |
| 3.11 | Approach Adept Consulting to check scope on surface water in common drains, check if capacity of sewage treatment is in scope and understand reduced terms if YW decline to engage | CE | 20th June | Complete 11/6 |
| 3.12 | Get approval from PC to spend up to £1,500 on Phase 1 of the Adept proposal subject to the above | PG | 16th June | Complete |
| 3.13 | Arrange tables / refreshments / table card holders for 20th June meeting | PG / RS | 20th June | Complete |
| 3.14 | Send out a meeting reminder – to our volunteer list + PC mailing list (via Steve) | JF | 15th June | Complete. |

- Project Management Update

DG shared the updated project plan (attached below) which was supported.

A useful discussion took place about the fundamental step of preparing the plan for each subject area.  It was agreed that:

Step 1 :		Define the “as is” with evidence-based data where possible : Target end 2026

Step 2 :		Recommend / draft the “so what” (i.e. the draft policies) based on the above.

We will aim for aspirational and very ambitious objectives in Step 2 – the subsequent consultation will determine how realistic / deliverable they are!  The recommendation now is “shoot for the stars”!

Sub-Groups will feedback their “Step 1” conclusions between October and December 2027.

- Finance

The Clerk has prepared a finance report which was circulated after the meeting.  This highlighted the importance of preparing a budget.

- Sub-Groups Update:

- Comms                                                 	JF

- The Comms plan (attached) was discussed and approved.

- The first Village Survey will focus on the draft (once approved) Housing Provision & Affordability questionnaire, with some additional questions added to support Flooding & Utilities Capacity.   CE / JH to complete consolidated draft

- Survey will  be based on households (not individuals) – 1 per household

- Hand-delivered – team / route needed

- Completion – paper and online (both) – IT solution needed

- Aim to send out in early September, complete by end of month (3 week survey time)

- It was agreed to purchase 4 noticeboards to provide info / progress on the NDP – ideally to be positioned in both churches, Village Hall and Pub

- Housing provision & affordability    JH

- See comments on survey above

- Update below:

- Heritage & local character               	RS

The History Group is now supporting the group (David Derbyshire).  A good first meeting.  Photos are being taken to support character recommendations.

- Flooding & utilities capacity             	CE

Adept have now approached YW for the Phase 1 data request.  PO still required? (Clerk).

It is accepted that the beck impacts on this group and Green Spaces – a joint meeting will be arranged.

YW have been doing significant data collection in the village recently.

- Transport & access              		RHW

The proposal to purchase traffic monitoring equipment was approved up to £800 total cost.  GDPR compliance was discussed.  It was agreed that detailed village communications should go out before the monitoring starts.  Also, a Highways Consultant should be approached to check the format of our data collection is appropriate for a future consultant-led report.

- Environment, Landscape & Water                                      	PC

Gypsum was discussed – the gypsum report will be referred to in the final NDP.

- Community facilities                          	RH

A good first meeting has been held, focussing on the school.  It was noted that the school is nearly full and 50% of students come from outside the Village.  Places cannot be ring fenced for villagers.  A summary of some of the background was circulated but will not be included in the published minutes due to confidentiality issues.

- AOB

None

- Date of next meeting

Wednesday 30th September at 7pm : Methodist School Room / Teams

(Action list on next page)

Actions

| # | Action | Who | When | Status |
| --- | --- | --- | --- | --- |
| Previous Meetings |  |  |  |  |
| 2.10 | Notify other stakeholders of the decision to produce a NP | Clerk | 15th May | DG to prepare a list of stakeholders – Complete. DG / JF to draft the letter – Complete. Sue to send out on behalf of the PC – Unsure – PG to chase. |
| 3.4 | Meet village organisations (e.g. WI, Coffee Mornings, Churches) to talk about NHP | JF / PG | Ongoing | Ongoing |
| 3.6 | Set up OneDrive account | PG | 30th June | Partially complete – PG to move to PC domain |
| 4th August 2026 Meeting |  |  |  |  |
| 4.1 | Sub-groups to feedback their “as is” conclusion data in our Oct / Nov / Dec meetings | Leaders | Dec 2026 | Proposal for which group at which meeting made |
| 4.2 | Send out budget pro-forma (PG) and complete (All) – to discuss at our next meeting. Need to identify and address any 2026/7 funding shortfalls. | All | End-August | Spreadsheet sent out. |
| 4.3 | Look at purchase of 4 noticeboards for NDP updates – both churches, pub, Village Hall (permission needed from all!) | JF | End-Sept |  |
| 4.4 | Prepare first village survey to address Housing Provision & Affordability – plus some questions on Utilities / Infrastructure. Check survey with our data expert. Make available in paper and online format. | JF / CE / JH | End August |  |
| 4.5 | Distribute / collect surveys | JF / Team | Sept (3 weeks) | Comms team volunteers to help delivery / collection |
| 4.6 | PO Required for Adept | Clerk | August 10th |  |
| 4.7 | Drainage / Utilities Group to approach c.10 stakeholders for info / opinions | CE | September 15th | Need to confirm Stakeholder communications have gone out first (2.10) |
| 4.8 | Joint meeting needed between Flooding / Utilities & Green Spaces groups to discuss the beck | CE / PC | End-Sept |  |
| 4.9 | Purchase traffic monitoring equipment (Amazon) | RHW / Clerk | Immediately |  |
| 4.10 | Village communications for traffic monitoring starts | RHW / JF | August |  |
| 4.11 | Identify Highways Consultant to give opinion on our traffic counting proposal | DG / RHW | August |  |

P Goodier

6th August 2026