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Neighbourhood Plan Working Group
Agenda for our Fourth Meeting: Wednesday 30th September at 7pm
Methodist School Room / Teams

1. Apologies for absence
2. Agree minutes of last meeting (attached)
3. Feedback from September Parish Council meeting (approvals etc.)
4. Matters arising / actions review
	#
	Action
	Who
	When
	Status

	Previous Meetings

	2.10
	Notify other stakeholders of the decision to produce a NP
	Clerk
	15th May
	DG to prepare a list of stakeholders – Complete.
DG / JF to draft the letter – Complete.
Sue to send out on behalf of the PC – Complete & Replies on the server

	3.4
	Meet village organisations (e.g. WI, Coffee Mornings, Churches) to talk about NHP
	JF / PG
	Ongoing
	Ongoing

	3.6
	Set up OneDrive account
	PG
	30th June
	Partially complete – PG to move to PC domain

	
4th August  2026 Meeting

	4.1
	Sub-groups to feedback their “as is” conclusion data in our Oct / Nov / Dec meetings
	Leaders
	Dec 2026
	Proposal for which group at which meeting made

	4.2
	Send out budget pro-forma (PG) and complete (All) – to discuss at our next meeting.
Need to identify and address any 2026/7 funding shortfalls.
	All
	End-August
	Spreadsheet completed.

Shared with PC clerk

	4.3
	Look at purchase of 4 noticeboards for NDP updates – both churches, pub, Village Hall (permission needed from all!)
	JF
	End-Sept
	Complete except for pub

	4.4
	Prepare first village survey to address Housing Provision & Affordability – plus some questions on Utilities / Infrastructure.
Check survey with our data expert.
Make available in paper and online format.
	JF / CE / JH
	End August
	Live

	4.5
	Distribute / collect surveys
	JF / Team
	Sept (3 weeks)
	Complete / ongoing 

	4.6
	PO Required for Adept
	Clerk
	August 10th
	

	4.7
	Drainage / Utilities Group to approach c.10 stakeholders for info / opinions
	CE
	September 15th
	Need to confirm Stakeholder communications have gone out first (2.10)

	4.8
	Joint meeting needed between Flooding / Utilities & Green Spaces groups to discuss the beck
	CE / PC
	End-Sept
	

	4.9
	Purchase traffic monitoring equipment (Amazon) 
	RHW / Clerk
	Immediately
	Complete 

	4.10
	Village communications for traffic monitoring starts 
	RHW / JF
	August
	Complete

	4.11
	Identify Highways Consultant to give opinion on our traffic counting proposal
	DG / RHW
	August
	



5. Project Management           				DG
6. Implications of the new NPPF			DG / All
7. Parish Council Approvals / Communications process / link to TOR	PG
8. Sub-Groups Update:
a. Comms                                                  		JF
b. Housing provision & affordability    	JH
c. Heritage & local character               		RS
d. Flooding & utilities capacity             		CE         
e. Transport & access              			RHW
f. Green spaces                                       		PC
g. Community facilities                          		RH

9. AOB
10. Dates of next meetings in 2026
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