Neighbourhood Plan Working Group

Agenda for our Fourth Meeting: Wednesday 30th September at 7pm

Methodist School Room / Teams

- Apologies for absence

- Agree minutes of last meeting (attached)

- Feedback from September Parish Council meeting (approvals etc.)

- Matters arising / actions review

| # | Action | Who | When | Status |
| --- | --- | --- | --- | --- |
| Previous Meetings |  |  |  |  |
| 2.10 | Notify other stakeholders of the decision to produce a NP | Clerk | 15th May | DG to prepare a list of stakeholders – Complete. DG / JF to draft the letter – Complete. Sue to send out on behalf of the PC – Complete & Replies on the server |
| 3.4 | Meet village organisations (e.g. WI, Coffee Mornings, Churches) to talk about NHP | JF / PG | Ongoing | Ongoing |
| 3.6 | Set up OneDrive account | PG | 30th June | Partially complete – PG to move to PC domain |
| 4th August 2026 Meeting |  |  |  |  |
| 4.1 | Sub-groups to feedback their “as is” conclusion data in our Oct / Nov / Dec meetings | Leaders | Dec 2026 | Proposal for which group at which meeting made |
| 4.2 | Send out budget pro-forma (PG) and complete (All) – to discuss at our next meeting. Need to identify and address any 2026/7 funding shortfalls. | All | End-August | Spreadsheet completed. Shared with PC clerk |
| 4.3 | Look at purchase of 4 noticeboards for NDP updates – both churches, pub, Village Hall (permission needed from all!) | JF | End-Sept | Complete except for pub |
| 4.4 | Prepare first village survey to address Housing Provision & Affordability – plus some questions on Utilities / Infrastructure. Check survey with our data expert. Make available in paper and online format. | JF / CE / JH | End August | Live |
| 4.5 | Distribute / collect surveys | JF / Team | Sept (3 weeks) | Complete / ongoing |
| 4.6 | PO Required for Adept | Clerk | August 10th |  |
| 4.7 | Drainage / Utilities Group to approach c.10 stakeholders for info / opinions | CE | September 15th | Need to confirm Stakeholder communications have gone out first (2.10) |
| 4.8 | Joint meeting needed between Flooding / Utilities & Green Spaces groups to discuss the beck | CE / PC | End-Sept |  |
| 4.9 | Purchase traffic monitoring equipment (Amazon) | RHW / Clerk | Immediately | Complete |
| 4.10 | Village communications for traffic monitoring starts | RHW / JF | August | Complete |
| 4.11 | Identify Highways Consultant to give opinion on our traffic counting proposal | DG / RHW | August |  |

- Project Management           				DG

- Implications of the new NPPF			DG / All

- Parish Council Approvals / Communications process / link to TOR	PG

- Sub-Groups Update:

  - Comms                                                  		JF

  - Housing provision & affordability    	JH

  - Heritage & local character               		RS

  - Flooding & utilities capacity             		CE

  - Transport & access              			RHW

  - Green spaces                                       		PC

  - Community facilities                          		RH

- AOB

- Dates of next meetings in 2026